## Onam Summary
ONAM 2026 – PLANNING SUMMARY
Note | All figures are simulated planning data for a portfolio/learning project, not actual event results.
Onam Date | 2026-08-26
Total Activities
Expected Participants
Estimated Budget
Budget Spent
Remaining Budget
Budget Utilization %
Completed Activities
In Progress Activities
Not Started Activities
Average Preparation Progress %

## Read Me
ONAM 2026 – POWER BI DATASET
Purpose | Sample planning data for an Onam 2026 Preparation & Celebration Dashboard.
Important | This is simulated/sample data created for a learning portfolio. It does not represent actual event statistics.
Suggested Power BI relationships
Activities[Date] | → Calendar[Date]
Activities[ActivityID] | → Participants[EventPreference] cannot be directly related; use Activity as a common dimension or create an Event dimension.
Recommended KPIs | Total Activities, Expected Participants, Estimated Budget, Completed Activities, Locations
Recommended visuals | Timeline, Budget by Category, Preparation Status, Estimated Cost by Activity, Expected Participants by Activity, Events by Location
Onam date used | 26-Aug-2026 (Thiruvonam)

## Activities
ActivityID | Activity | Category | Date | Location | ExpectedParticipants | EstimatedCost | PreparationStatus | ActualCost | BudgetStatus | BudgetVariance | BudgetUtilizationPct | DaysBeforeOnam | Priority | ResponsibleTeam | PreparationProgressPct
1 | Pookalam | Cultural | 2026-08-17 | Main Hall | 80 | 5000 | Completed | 4500 | Near Budget | 500 | 90% | 9 | High | Cultural Committee | 100
2 | Onam Games | Games & Sports | 2026-08-18 | Ground | 100 | 8000 | Completed | 7500 | Near Budget | 500 | 93.75% | 8 | Medium | Games Committee | 100
3 | Thiruvathira | Cultural | 2026-08-20 | Auditorium | 60 | 10000 | In Progress | 6000 | Within Budget | 4000 | 60% | 6 | Medium | Cultural Committee | 50
4 | Sadya | Food & Sadya | 2026-08-22 | Dining Hall | 150 | 25000 | In Progress | 12000 | Within Budget | 13000 | 48% | 4 | High | Food Committee | 50
5 | Cultural Program | Cultural | 2026-08-24 | Auditorium | 120 | 15000 | In Progress | 3000 | Within Budget | 12000 | 20% | 2 | High | Cultural Committee | 50
6 | Thiruvonam Celebration | Cultural | 2026-08-26 | Main Hall | 250 | 35000 | Not Started | 0 | Not Spent | 35000 | 0% | 0 | High | Cultural Committee | 0
7 | Music Program | Entertainment | 2026-08-21 | Open Stage | 100 | 7000 | Not Started | 1500 | Within Budget | 5500 | 21.43% | 5 | Medium | Entertainment Team | 0
8 | Flower Arrangement | Decoration | 2026-08-19 | Main Hall | 50 | 5000 | Completed | 4800 | Near Budget | 200 | 96% | 7 | Medium | Decoration Team | 100
9 | Traditional Dress Contest | Games & Sports | 2026-08-23 | Auditorium | 50 | 3000 | In Progress | 2500 | Near Budget | 500 | 83.33% | 3 | Low | Games Committee | 50
10 | Quiz Competition | Games & Sports | 2026-08-23 | Classroom Block | 30 | 2000 | Not Started | 0 | Not Spent | 2000 | 0% | 3 | Low | Games Committee | 0
11 | Best Pookalam Contest | Cultural | 2026-08-25 | Open Stage | 40 | 3000 | In Progress | 1000 | Within Budget | 2000 | 33.33% | 1 | Medium | Cultural Committee | 50
12 | Prize Distribution | Prizes & Gifts | 2026-08-26 | Main Hall | 100 | 2000 | Not Started | 0 | Not Spent | 2000 | 0% | 0 | High | Event Committee | 0

## Budget
Category | EstimatedBudget | Status
Food & Sadya | 45000 | Planned
Decoration | 20000 | Planned
Cultural Programs | 25000 | Planned
Games & Sports | 15000 | Planned
Prizes & Gifts | 10000 | Planned
Others | 10000 | Planned

## Participants
ParticipantID | Name | Department | Age | Gender | EventPreference
1001 | Aarav | Data Analytics | 24 | Male | Pookalam
1002 | Ananya | Data Analytics | 27 | Female | Thiruvathira
1003 | Rahul | Python | 25 | Male | Onam Games
1004 | Meera | Power BI | 29 | Female | Cultural Program
1005 | Arjun | SQL | 26 | Male | Onam Games
1006 | Diya | Excel | 23 | Female | Pookalam
1007 | Vishnu | Data Analytics | 31 | Male | Sadya
1008 | Anjali | Power BI | 28 | Female | Thiruvathira
1009 | Nikhil | SQL | 30 | Male | Quiz Competition
1010 | Devika | Python | 26 | Female | Cultural Program
1011 | Kiran | Excel | 24 | Male | Traditional Dress Contest
1012 | Athira | Data Analytics | 27 | Female | Best Pookalam Contest
1013 | Sreejith | Power BI | 32 | Male | Thiruvonam Celebration
1014 | Lakshmi | SQL | 25 | Female | Sadya
1015 | Manu | Python | 29 | Male | Music Program

## Locations
Location | NumberOfActivities
Main Hall | 4
Auditorium | 2
Ground | 2
Dining Hall | 1
Open Stage | 1
Classroom Block | 1
Other Venues | 1

## Calendar
Date | Day | DayName | Week | Month | MonthNumber | IsOnamWeek
2026-08-01 | 1 | Saturday | 31 | August | 8 | FALSE
2026-08-02 | 2 | Sunday | 31 | August | 8 | FALSE
2026-08-03 | 3 | Monday | 32 | August | 8 | FALSE
2026-08-04 | 4 | Tuesday | 32 | August | 8 | FALSE
2026-08-05 | 5 | Wednesday | 32 | August | 8 | FALSE
2026-08-06 | 6 | Thursday | 32 | August | 8 | FALSE
2026-08-07 | 7 | Friday | 32 | August | 8 | FALSE
2026-08-08 | 8 | Saturday | 32 | August | 8 | FALSE
2026-08-09 | 9 | Sunday | 32 | August | 8 | FALSE
2026-08-10 | 10 | Monday | 33 | August | 8 | FALSE
2026-08-11 | 11 | Tuesday | 33 | August | 8 | FALSE
2026-08-12 | 12 | Wednesday | 33 | August | 8 | FALSE
2026-08-13 | 13 | Thursday | 33 | August | 8 | FALSE
2026-08-14 | 14 | Friday | 33 | August | 8 | FALSE
2026-08-15 | 15 | Saturday | 33 | August | 8 | FALSE
2026-08-16 | 16 | Sunday | 33 | August | 8 | FALSE
2026-08-17 | 17 | Monday | 34 | August | 8 | TRUE
2026-08-18 | 18 | Tuesday | 34 | August | 8 | TRUE
2026-08-19 | 19 | Wednesday | 34 | August | 8 | TRUE
2026-08-20 | 20 | Thursday | 34 | August | 8 | TRUE
2026-08-21 | 21 | Friday | 34 | August | 8 | TRUE
2026-08-22 | 22 | Saturday | 34 | August | 8 | TRUE
2026-08-23 | 23 | Sunday | 34 | August | 8 | TRUE
2026-08-24 | 24 | Monday | 35 | August | 8 | TRUE
2026-08-25 | 25 | Tuesday | 35 | August | 8 | TRUE
2026-08-26 | 26 | Wednesday | 35 | August | 8 | TRUE
2026-08-27 | 27 | Thursday | 35 | August | 8 | FALSE
2026-08-28 | 28 | Friday | 35 | August | 8 | FALSE
2026-08-29 | 29 | Saturday | 35 | August | 8 | FALSE
2026-08-30 | 30 | Sunday | 35 | August | 8 | FALSE
2026-08-31 | 31 | Monday | 36 | August | 8 | FALSE

## Budget Tracker
Category | Estimated Budget | Actual Spent | Variance | Utilization % | Budget Status
Cultural
Decoration
Entertainment
Food & Sadya
Games & Sports
Prizes & Gifts